## Sheet3
Key
Completed since last model update
Previously Completed
Outstanding
Theme | Feedback | Remarks | Resolution
Usability | 30 lines to input resources in ‘Capacity – Role Config’ worksheet is restrictive | Paul has extended this to 100 rows in a version sent to Andy Neal | Increased the amount of roles and lines of capacity that can be entered to 100.
| Permissible length of stream names is restrictive | Issue lies in VBA | Importing code changed to allow for longer stream names.
| Model doesn't export data if stream name has punctuation |  | Data Validation created for stream name to ensure no punctuation can be entered
Populating the model | Entry of historic data causing issue for hours / periods with no attendances | Extract demand data, put in a pivot table and ensure “show items with no data” is selected resolves this, also "for blank cells show:" (zero) | Team to raise awareness of the issue, and can advise on how to make sure that all hours are represented in the data. This can be achieved by using a pivot table in Excel, if users are unfamiliar with SQL resolution.
| Can see difficulty in populating the staffing part of the tool, due to not having e-rosters | Mentioned by a BI colleague. Need to be crystal clear that this is an operational model, requiring collaboration between BI, operationsal and clinical colleagues. Operational / clinical colleagues will have access to rota info, even if there is no e-roster. Regardless, it is expected that capacity information is validated by clinical / operational colleagues. No working in silos! | The model is designed to be used as a collaboration between a number of different trust users, such as BI, operational colleagues and clinical staff. Operational managers should be able to complete the rota information if it is not held on an e-roster programme.
| Shift Unfilled should also be an option on each daily entry |  | To be confirmed
| Parameters should be set by stream |  | To be confirmed
| Streams have to be imported together, otherwise previous imports are overwritten |  | To be confirmed
Interface | Cell reference error, when entering streams | This refers to the validation list in "view stream" dropdown in the "Demand Analysis" worksheet | This was happening when stream names were changed part way through model completion. This has now been corrected in the latest version, with charts reverting to the first stream entered if it detects changes in any of the stream names.
| Chart in 'CDMH - capacity' worksheet may be confusing |  | Additional information has been added to the sheet to help users understand what the chart is showing.
| Day differentiation not clear with only every second hour being displayed |  | Interface to be improved by making daily distinctions clearer
| Summary table needs a key for colours |  | Interface to be improved by adding a key
| Queue builder needs a key for colours, and can we be clearer about what it is showing? |  | Interface to be improved by adding a key, and think about wording around 'risk' for explanation.
| Not obvious how to use forecasting app, such as how to upload a file, set the opening times etc. |  | Interface to be improved (numbered steps, for example), as well as possible to do a small video tutorial?
Outputs | Is it possible to have a summary of all streams (and weekdays) on the summary worksheet? | Re: all streams, perhaps total demand as CDMH vs total capacity as CDMH? Not sure how useful it is looking at entire week | Two changes made to outputs. 1. All days can be seen in the chart as well as the heatmap now. 2. All streams can be seen in the chart and the heatmap, with an appropriate warning flag to say that this view may be misleading.
| Graphs / charts are behaving unexpectedly - eg. populate model working fine on our computers, but graphs are blank when the same file is opened on stakeholders' computers |  | Issue with pre-2016 Excel versions not being able to read two columns of data for x-axis. Fixed by creating a new named range.
| Is it possible to provide a daily/weekly summary? |  | To be confirmed
Scope | Capability of the model to look at triage capacity has been mentioned multiple times | An eg. from an (MIU) setting - a Roster may say 10 people, however only 6 are treating, 2 are triaging, etc - to consider? | No current resolution devised. This needs to be discussed internally and scoped out, with a potential update to the model coming at a later time.
| Can the model look at longer term? Eg. to plan cover for leave |  | Not within the scope of this model. Longer term alternatives are available from the ECIST team, and work is being done in other teams in NHSI/E for staffing ED departments in the longer term.
| Need to be crystal clear about the scope of the model, ie an operational tool to ensure patients are seen by a CDM (and what this means), within an hour of arrival | One stakeholder only referred to consultants. Perhaps we need to define what we mean by clinical decision making and clinical decision maker, ie, not only consultants. Also triage has been mentioned multiple occasions (as above) - to consider further. | Additional front page information has been created for the model, to help explain the scope and the purpose of the model.
Configuration | Query received whether minutes per stream needs to be entered on demand entry sheet | These highlight the need for clarity in documentation as to the purpose of these fields, ie: minutes per stream = on average how long it takes to treat a patient. We also need to be clear that this info, as well as the time per clinician / stream needs to be obtained by having discussion with clinicans and operational staff - not BI working in silos | Additional front page information has been added to help clarify the scope of the model. Additional information on how to source some of the data requirements may be needed, and will be added to supporting documentation.
| Query received about obtaining CDM time by clinician from systems |  | Additional front page information has been added to help clarify the scope of the model. Additional information on how to source some of the data requirements may be needed, and will be added to supporting documentation.
| Shift configuration does not account for statutory meal breaks |  | To be confirmed
Other | Suggestion that forecasting methodology is picking up the difference in arrival profiles by day of week | To discuss in webinar | Team to design templates for users to enter their own forecasting in to.
Operational | Do users need to see the demand analysis tab? |  | Helps tell the data 'story', as well as sense check forecasting outputs against expected.
| Each role may have shift types that vary in time and length. |  | Can configure 30 in the tool, and should be raising questions if departments are working in this way.
| Concerns about how organisations can identify the 'productivity' of the roles. |  | Team will ensure we link in with work in other teams around defining these values.
| 'Clinical decisions per hour' could potentially be misleading |  | Documentation within model to be clarified.
| What does priority mean, and what impact does it have? |  | Further clarification has been written for within the model, however additional guidance may need to be produced.
| How can we measure impact of the model? |  | Feedback loop for checking accuracy of model to be scoped.